## LABOUR
LABOUR DETAILS - 2025
SL NO | DATE | DESCRIPTION | HEAD | REMARKS
1 | 2025-11-01 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
2 | 2025-11-02 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
3 | 2025-11-03 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
4 | 2025-11-04 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
5 | 2025-11-05 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
6 | 2025-11-06 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN,SAMSUDDIN,DIPAK DHALAI -4 | 8 | GP
7 | 2025-11-07 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
8 | 2025-11-08 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
9 | 2025-11-09 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN,PRALLAD M-1,L-2 | 6 | GP
10 | 2025-11-10 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
11 | 2025-11-11 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
12 | 2025-11-12 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
13 | 2025-11-13 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
14 | 2025-11-14 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
15 | 2025-11-15 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
16 | 2025-11-16 | SUDHIR,SAIFUDDIN | 2 | GP
17 | 2025-11-17 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | GP
18 | 2025-11-18 | NO
19 | 2025-11-19 | NO
20 | 2025-11-20 | NO
21 | 2025-11-21 | NO
22 | 2025-11-22 | NO
23 | 2025-11-23 | NO
24 | 2025-11-24 | NO
25 | 2025-11-25 | NO
26 | 2025-11-26 | NO
27 | 2025-11-27 | NO
28 | 2025-11-28 | NO
29 | 2025-11-29 | NO
30 | 2025-11-30 | NO
31 | 2025-12-01 | SUDHIR,SAIFUDDIN | 2 | GP
32 | 2025-12-02 | MIJANUR L -1 ,SUDHIR | 2 | GP
33 | 2025-12-03 | NO
34 | 2025-12-04 | AMARESH,KHOKHAN | 2 | GP
35 | 2025-12-05 | NO
36 | 2025-12-06 | AMARESH | 1 | GP
37 | 2025-12-07 | SUDHIR,PRALLAD L -1 | 2 | GP
38 | 2025-12-08 | NO
39 | 2025-12-09 | NO
40 | 2025-12-10 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | OFC
41 | 2025-12-11 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | OFC
42 | 2025-12-12 | MIJANUR L -1 ,SUDHIR,SAIFUDDIN | 3 | OFC
43 | 2025-12-13 | NO
44 | 2025-12-14 | SAIFUDDIN HALF DAY
45 | 2025-12-15 | NO
46 | 2025-12-16 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
47 | 2025-12-17 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
48 | 2025-12-18 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
49 | 2025-12-19 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
50 | 2025-12-20 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
51 | 2025-12-21 | NO
52 | 2025-12-22 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
53 | 2025-12-23 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
54 | 2025-12-24 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
55 | 2025-12-25 | MIJANUR M-1 L -1 ,SUDHIR,SAIFUDDIN | 4 | OFC
56 | 2025-12-26 | NO
57 | 2025-12-27 | SUDHIR,SAIFUDDIN | 2 | OFC
58 | 2025-12-28 | NO
59 | 2025-12-29 | NO
60 | 2025-12-30 | SUDHIR | 1 | OFC
61 | 2025-12-31
Lab - 2026
1 | 2026-02-01 | Sudhir,Saifuddin | 2
2 | 2026-02-02 | no
3 | 2026-02-03 | no
4 | 2026-02-04 | no
5 | 2026-02-05 | Sudhir,Samuddin | 2
6 | 2026-02-06 | Sudhir,Samuddin | 2
7 | 2026-02-07 | No
8 | 2026-02-08 | Subid kaka,Prallad | 2
9 | 2026-02-09 | Subid kaka | 1
10 | 2026-02-10 | Sudhir,Saifuddin,Subid kaka | 3
11 | 2026-02-11 | no
12 | 2026-02-12 | Sudhir,Saifuddin,Subid kaka,Samuddin | 4
13 | 2026-02-13 | Sudhir,Saifuddin,Subid kaka,Samuddin | 4
14 | 2026-02-14 | Sudhir,Saifuddin,Subid kaka,Samuddin,DIPAK | 6
15 | 2026-02-15 | Sudhir,Samuddin | 2
16 | 2026-02-16 | no
17 | 2026-02-17 | Sudhir,Saifuddin,Subid kaka,PRADIP L -2 | 5
18 | 2026-02-18 | Sudhir,Saifuddin | 2
19 | 2026-02-19 | no
20 | 2026-02-20 | no
21 | 2026-02-21 | no
22 | 2026-02-22 | no
23 | 2026-02-23 | no
| 2026-02-24 | no
| 2026-02-25 | no
| 2026-02-26 | no
| 2026-02-27 | no
| 2026-02-28 | no
| 2026-03-01 | no
| 2026-03-02 | no
| 2026-03-03 | no
| 2026-03-04 | no
| 2026-03-05 | no
| 2026-03-06 | Sudhir,Subid | 2
| 2026-03-07 | subid,pradip l -2 | 3
| 2026-03-08 | no
| 2026-03-09 | no
| 2026-03-10 | no
| 2026-03-11 | no
| 2026-03-12 | no
| 2026-03-13 | no
| 2026-03-14 | no
| 2026-03-15 | no
| 2026-03-16 | no
| 2026-03-17 | no
| 2026-03-18 | no
| 2026-03-19 | Sarfuddin,Subid | 2
| 2026-03-20 | Subid,Prallad l -1 | 2
| 2026-03-21 | no
| 2026-03-22 | no
| 2026-03-23 | no
| 2026-03-24 | Sudhir,Pradip L-1,Prallad L-4 | 6
| 2026-03-25 | Sudhir,Prallad L-3 | 4
| 2026-03-26 | sudhir,pradip l-1 | 2
| 2026-03-27 | sudhir,pradip l-2,dipak 4 | 7
| 2026-03-28 | sudhir,pradip l-2,mizanur m-1,l-1 | 5
| 2026-03-29 | sudhir,Sarfuddin.subid,Pradip m-1,l-1 | 5
| 2026-03-30 | PRADIP L -2,SABIR | 3
| 2026-03-31 | SUDHIR,SUBID,SARFUDDIN,PRADIP L-2 | 5
| 2026-04-01 | SUDHIR,SUBID,SARFUDDIN | 3
| 2026-04-02 | no
| 2026-04-03 | Sudhir,Pradip L-2 | 3
| 2026-04-04 | SUDHIR,SUBID,SARFUDDIN,PRADIP L-1 | 4
| 2026-04-05 | Prallad M-1,L-1 | 2
| 2026-04-06 | Sarfuddin,Subid,sudhir | 3
| 2026-04-07 | SUDHIR,SUBID,SARFUDDIN,PRADIP L-2 | 5
| 2026-04-08 | SUBID,SARFUDDIN, | 2
| 2026-04-09 | SARFUDDIN,SS LAB - 2 | 3
| 2026-04-10 | sarfuddin,prallad l-1,subid | 3
| 2026-04-11 | sarfuddin,prallad m-1 l-1,subid | 4
| 2026-04-12 | sarfuddin,sudhir,subid | 3
| 2026-04-13 | subid,anada l-2 | 3
| 2026-04-14 | anada l-1,subid,pradip | 3
| 2026-04-15 | SARFUDDIN,SUDHIR,SUBID,PRADIP L3 | 6
| 2026-04-16 | SARFUDDIN,SUDHIR,SUBID | 3
| 2026-04-17 | SALBOLLA 7,SUBID | 8
| 2026-04-18 | SALBOLLA 8,SUBID | 9
| 2026-04-19 | SALBOLLA 8,SUBID,SAIFUDDIN | 10
| 2026-04-20 | SALBOLLA 8,SUBID,SAIFUDDIN | 10
| 2026-04-21 | ,SAIFUDDIN | 1
| 2026-04-22 | SALBOLLA 8,SUBID,ALON 2 | 11
| 2026-04-23 | SALBOLLA 8,SUBID | 9
| 2026-04-24 | SALBOLLA 6,SUBID | 7
| 2026-04-25 | SALBOLLA 6,SUBID,SAIFUDDIN | 8
| 2026-04-26 | SALBOLLA 6,SUBID | 7
| 2026-04-27 | SAIFUDDIN | 1
2026-04-28
2026-04-29
| 2026-04-30 | Sudhir Kaka | 1
| 2026-05-01 | Sudhir Kaka,Subid | 2
2026-05-02
2026-05-03
2026-05-04
2026-05-05
| 2026-05-06 | Sudhir Kaka,Subid,Saifuddin | 3
| 2026-05-07 | Sudhir Kaka,Subid,Saifuddin | 3
2026-05-08
2026-05-09
2026-05-10
2026-05-11
2026-05-12
2026-05-13
2026-05-14
2026-05-15
2026-05-16
2026-05-17
| 2026-05-18 | subid - night | 1
| 2026-05-19 | Sudhir Kaka,Saifuddin,subid - night | 3
| 2026-05-20 | Sudhir Kaka,prallad l-2 | 3
2026-05-21
2026-05-22
2026-05-23
2026-05-24
2026-05-25
2026-05-26
2026-05-27
2026-05-28
2026-05-29
2026-05-30
| 2026-05-31 | samsuddin,subid,sarfuddin | 3
| 2026-06-01 | mijanur m-2,l-5,sabir | 8
| 2026-06-02 | mijanur m-2,l-3,samsuddin,sabir | 5
| 2026-06-03 | mijanur m-1,l-4,samsuddin,sabir | 7
| 2026-06-04 | mijanur m-2,l-5,samsuddin,sabir | 9
| 2026-06-05 | mijanur m-2,l-4,subid,sabir | 8
| 2026-06-06 | mijanur m-2,l-4,samsuddin
2026-06-07
2026-06-08
2026-06-09
2026-06-10
2026-06-11
2026-06-12
2026-06-13
2026-06-14
2026-06-15
2026-06-16
2026-06-17
2026-06-18
2026-06-19
2026-06-20

## CEMENT
CEMENT (APRIL)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2022-04-28 | BANSAL TO GREEN PLY (RAJU TEMPO) | JSW | 3
2 | 2022-04-29 | BANSAL TO GREEN PLY | JSW | 3
3 | 2022-04-30 | BANSAL TO GREEN PLY | ? | 5
CEMENT (MAY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2022-05-01 | OFFICE TO GREEN PLY | ? | 25
2 | 2022-05-14 | OFFICE TO GREEN PLY | JSW | 5
3 | 2022-05-15 | OFFICE TO GREEN PLY | JSW | 20
4 | 2022-05-21 | OFFICE TO GREEN PLY | JSW | 21
CEMENT (JULY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2022-07-04 | BANSAL TO GREEN PLY |  | 3
2 | 2022-07-10 | BANSAL TO GREEN PLY |  | 4
3 | 2022-07-31 | BANSAL TO GREEN PLY |  | 3
CEMENT (AUG)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2022-08-15 | BANSAL TO GREEN PLY |  | 3BAG
CEMENT (OCT & NOV)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2022-10-04 | BANSAL TO G.PLY | ULTRATECH | 3
2 | 2022-10-11 | BANSAL TO G.PLY | CEMENT | 1 BAG | TILL | 99 BAG
3 | 2022-10-14 | SS OFFCIE TO G.PLY | ULTRATECH | 5 BAG
4 | 2022-10-16 | SALAPURIA TO G.PLY | ULTRATECH | 3 BAG
5 | 2022-11-13 | SALAPURIA TO G.PLY | JSW | 7 BAG
6 | 2022-11-17 | SALAPURIA TO G.PLY | JSW | 14 BAG
7 | 2022-11-18 | SALAPURIA TO G.PLY | JSW | 3 BAG
8 | 2022-11-19 | SALAPURIA TO G.PLY | JSW | 4 BAG
9 | 2022-11-20 | SALAPURIA TO G.PLY | JSW | 4 BAG
CEMENT (DEC)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2022-12-16 | SALAPURIA TO G.PLY | JSW | 1 BAG
2 | 2022-12-24 | SALAPURIA TO G.PLY | JSW | 6 BAG
3 | 2022-12-30 | SALAPURIA TO G.PLY | ULTRATECH | 7 BAG
4 | 2022-12-31 | SALAPURIA TO G.PLY | ULTRATECH | 7 BAG
CEMENT (JAN 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-01-01 | SALAPURIA TO G.PLY |  | 1 BAG
2 | 2023-01-08 | SALAPURIA TO G.PLY |  | 1 BAG
3 | 2023-01-22 | SALAPURIA TO G.PLY | JSW | 4 BAG
4 | 2023-01-26 | SALAPURIA TO G.PLY | JSW | 15BAG
CEMENT (FEB 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-02-26 | SALAPURIA TO G.PLY | JSW | 16BAG
2
3
4
CEMENT (MAR 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-03-12 | SALAPURIA TO GREEN PLY |  | 4 BAG
2 | 2023-03-15 | SALAPURIA TO GREEN PLY |  | 4 BAG
3 | 2023-03-19 | SALAPURIA TO GREEN PLY |  | 4 BAG
4
CEMENT (APRIL 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-04-09 | SS OFFICE TO GREEN PLY | JSW | 15 BAG
2 | 2023-04-16 | SALAPURIA TO GREEN PLY | JSW | 4 BAG
3 | 2023-04-26 | SS OFFICE TO GREEN PLY | JSW | 14 BAG
4
CEMENT (APRIL 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-05-01 | RINKU TO GREEN PLY | DALMIA | 11 BAG
CEMENT (MAY 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-05-24 | RINKU TO GREEN PLY | ULTRATECH | 3 BAG
2 | 2023-05-25 | SALAPURIA TO GREEN PLY | ULTRATECH | 3 BAG
3 | 2023-05-28 | RINKU TO GREEN PLY | ULTRATECH | 7 BAG
CEMENT (JUNE 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-06-04 | RINKU TO GREEN PLY | ULTRATECH | 5 BAG
2 | 2023-06-12 | RINKU TO GREEN PLY | ULTRATECH | 4 BAG
3 | 2023-06-15 | RINKU TO GREEN PLY | ULTRATECH | 12 BAG
4 | 2023-06-17 | RINKU TO GREEN PLY | ULTRATECH | 12 BAG
5 | 2023-06-18 | RINKU TO GREEN PLY | ULTRATECH | 10 BAG
6 | 2023-06-25 | RINKU TO GREEN PLY | ULTRATECH | 6 BAG
CEMENT (JULY 2023) | [5 empty] | CEMENT (JULY 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG) |  | SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-07-02 | RINKU TO GREEN PLY | ULTRATECH | 6 BAG |  | 1 | 2023-07-06 | GREEN PLY TO AUSTIN | ULTRATECH | 6 BAG
2 | 2023-07-14 | RINKU TO GREEN PLY | ULTRATECH | 1 BAG
3 | 2023-07-29 | RINKU TO GREEN PLY | ULTRATECH | 4 BAG
4 | 2023-07-31 | RINKU TO GREEN PLY | ULTRATECH | 1 BAG
CEMENT(AUG-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-08-15 | RINKU BUILDERS TO GREEN PLY |  | 3 BAG
2 | 2023-08-20 | RINKU BUILDERS TO GREEN PLY 2NO |  | 2 BAG
3
CEMENT(SEP-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-09-05 | RINKU BUILDERS TO GREEN PLY |  | 2 BAG
2 | 2023-09-13 | RINKU BUILDERS TO GREEN PLY |  | 1 BAG
3 | 2023-09-14 | RINKU BUILDERS TO GREEN PLY |  | 2 BAG
4 | 2023-09-15 | RINKU BUILDERS TO GREEN PLY 2NO |  | 7 BAG
5 | 2023-09-16 | RINKU BUILDERS TO GREEN PLY 2NO |  | 3 BAG
6 | 2023-09-20 | RINKU BUILDERS TO GREEN PLY 2NO |  | 3 BAG
7 | 2023-09-21 | RINKU BUILDERS TO GREEN PLY 2NO |  | 4 BAG
8 | 2023-09-22 | RINKU BUILDERS TO GREEN PLY 2NO |  | 4 BAG
9 | 2023-09-24 | RINKU BUILDERS TO GREEN PLY 2NO |  | 4 BAG
10 | 2023-09-25 | RINKU BUILDERS TO GREEN PLY 2NO |  | 6 BAG
11 | 2023-09-26 | RINKU BUILDERS TO GREEN PLY 2NO |  | 5 BAG
12 | 2023-09-29 | RINKU BUILDERS TO GREEN PLY 2NO |  | 5 BAG
CEMENT(OCT-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-10-05 | RINKU BUILDERS TO GREEN PLY 2NO |  | 4 BAG
2 | 2023-10-06 | RINKU BUILDERS TO GREEN PLY 2NO |  | 4 BAG
3 | 2023-10-18 | RINKU BUILDERS TO GREEN PLY 2NO |  | 6 BAG
4 | 2023-10-21 | RINKU BUILDERS TO GREEN PLY |  | 6 BAG
5 | 2023-10-22 | SS OFFICE TO GREEN PLY |  | 5 BAG
6 | 2023-10-25 | SS OFFICE TO GREEN PLY |  | 5
CEMENT(NOV-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-11-10 | SS OFFICE TO GREEN PLY 2NO |  | 5 BAG
2 | 2023-11-13 | SS OFFICE TO GREEN PLY 2NO |  | 5 BAG
3 | 2023-11-17 | SS OFFICE TO GREEN PLY 2NO |  | 2 BAG
CEMENT(DEC-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2023-12-17 | DALMIA TO GREEN PLY | ULTRATECH | 1
CEMENT(FEB-2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2024-02-11 | DALMIA TO GREEN | ULTRATECH | 2
CEMENT(MAR-2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2024-03-24 | SS TO GREEN PLY | ULTRATECH | 25
CEMENT(AUG-2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2024-08-11 | RAMKRISHNAPUR TO GREEN PLY | ULTRATECH | 2
2 | 2024-08-15 | PAPPU TO GREEN | - | 3
3 | 2024-08-21 | PAPPU TO GREEN | - | 3
4 | 2024-08-23 | PAPPU TO GREEN |  | 5
6 | 2024-08-28 | LNB TO GREEN PLY | - | 2
CEMENT(AUG-2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2024-09-08 | RAMKRISHNAPUR TO GREEN PLY | - | 5
NEW PHASE - 25 NOV
CEMENT
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2025-11-06 | LNB TO GP | ULTRATECH | 25
2 | 2025-11-09 | RINKU TO GP | ULTRATECH | 12
| 2025-11-15 | RINKU TO GP | ULTRATECH | 2
| 2025-11-17 | RINKU TO GP | ULTRATECH | 4
CEMENT
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2026-02-08 | Sp to Gp |  | 3
2 | 2026-02-12 | Sp to Gp |  | 3
| 2026-02-13 | Sp to Gp |  | 10
| 2026-03-25 | Sp to Gp |  | 21

## TMT
TMT(MAY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND (SIZE) | DETAILS (PCS)
1 | 2022-05-04 | BANIR POLE TO G.PLY | 10 MM (9.5FT) | 11
|  |  | 10MM(5.5 FT) | 20
2 | 2022-05-07 | BISHNUPUR TO G.PLY | 10 MM (4 BANDLE) | 32
3 | 2022-05-23 | BANSAL TO GREEN PLY | 12 MM | 1 |  | 10 MM | 63
[6 empty] | 12 MM | 3
TMT(JULY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND (SIZE) | DETAILS (PCS)
1 | 2022-07-04 | BANSAL TO GREEN PLY | 12 MM | 1 PCS
2 | 2022-07-31 | BANSAL TO GREEN PLY | 12 MM | 1 PCS | TILL
TMT(NOV)
SR NO | DATE | FROM WHERE TO WHERE | BRAND (SIZE) | DETAILS (PCS)
1 | 2022-11-06 | SALAPURIA TO G.PLY | 10MM | 14P
2 | 2022-11-17 | SALAPURIA TO G.PLY | 10 MM | 58P
TMT(DEC)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS) | CAR NO
1 | 2022-12-24 | SALAPURIA TO GREEN PLY | 5.5MM | 23P
|  |  | 9.5MM | 12P
2 | 2022-12-30 | SALAPURIA TO GREEN PLY | 10 MM | 20FT -12P , 2FT - 14P, 4 FT - 25P
TMT(JAN-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND (SIZE) | DETAILS (PCS)
1 | 2023-01-26 | SALAPURIA TO G.PLY | 10MM | 46INCH -41P,20.5 -9P,6.5-4P
TMT(FEB-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND (SIZE) | DETAILS (PCS)
1 | 2023-02-26 | SALAPURIA TO G.PLY | 10 MM | 13P
TMT(MAR-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND (SIZE) | DETAILS (PCS)
1 | 2023-03-15 | SS OFFICE TO GREEN PLY | 10 MM | 3 BUNDLE
TMT(APRIL-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND (SIZE) | DETAILS (PCS)
1 | 2023-04-09 | SS OFFICE TO GREEN PLY | 10 MM | 6P
2 | 2023-04-15 | SS OFFICE TO GREEN PLY | 10 MM | 2 BUNDLE
TMT(MAY-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND (SIZE) | DETAILS (PCS)
1 | 2023-05-01 | SS OFFICE TO GREEN PLY | 10 MM | 2 BUNDLE
2 | 2023-05-26 | SALAPURIA TO GREEN PLY | 16MM | 5P
TMT(JUNE 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-06-13 | SS OFFICE TO GREEN PLY | 14' | 10
|  |  | 6' | 27
|  |  | 7' | 74
|  |  | 14.6' | 22
|  |  | 6.6' | 22
2 | 2023-06-24 | SS OFFICE TO GREEN PLY | PALLATE | 14 NOS(SR-1 TO 14) | SIRAJ HATI -WB19G4852
|  |  |  | 14 NOS(SR-29 TO 42) | SIRAJ HATI -WB19G4852
3 | 2023-06-27 | SS OFFICE TO GREEN PLY | PALLATE | 14 NOS (SR-42-56) | SIRAJ HATI -WB19L1006
|  |  | PALLATE | 14 NOS (SR-56-70) | SIRAJ HATI -WB19L1006
|  |  | PALLATE | 14 NOS (SR-70-84) | SIRAJ HATI -WB19L1006
TMT(JULY 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-07-03 | SS OFFICE TO GREEN PLY | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
|  |  | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
|  |  | PALLATE | 14 NO | SIRAJ HATI -WB19G4852
2 | 2023-07-04 | SS OFFICE TO GREEN PLY | PALLATE | 14 NO | SIRAJ HATI -WB19G4852
|  |  | PALLATE | 14 NO | SIRAJ HATI -WB19G4852
|  |  | PALLATE | 14 NO | SIRAJ HATI -WB19G4852
3 | 2023-07-19 | SS OFFICE TO GREEN PLY | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
|  |  | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
|  |  | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
4 | 2023-07-20 | SS OFFICE TO GREEN PLY | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
|  |  | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
5 | 2023-07-28 | SS OFFICE TO GREEN PLY | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
|  |  | PALLATE | 14 NO | SIRAJ HATI -WB19L1006
TMT(OCT-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-10-06 | 10 FT SHEET |  | 13
|  | 8 FT SHEET |  | 8
|  | SELF SCREW |  | 250
2 | 2023-10-20 | SS OFFICE TO GREEN PLY | 12 MM | 68" - 27 P
12'11" - 13P
3 | 2023-10-22 | RAMKRISHNAPUR TO GREEN PLY | 12 MM | 4P
|  |  | RING | 32P
TMT(NOV-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-11-01 | AUSTIN TO GREEN | 8 MM | 16
TMT(SEP-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-11-01 | RAMKRISHNAPUR TO GREEN | 10 MM | 104 | FT (8FT * 13P)
|  |  | 10 MM | 102 | FT (6FT * 17P)
NEW PHASE NOV-25
TMT
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2025-11-03 | JIT TO GREENPLY | 12 MM | 17
|  |  | 8 MM | 6
|  |  | 16 MM | 3
2 | 2026-02-13 | SP TO GP | 12 MM | 10
| 2026-03-25 | SP TO GP | JAIL /COLOUM

## SAND
SAND(APRIL)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2022-04-28 | BANSAL TO G.PLY (RAJU TEMPO) | SAND | 25 BAG
2 | 2022-04-29 | BANSAL TO G.PLY (TARAK) | SAND | 25 BAG
SAND(MAY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2022-05-01 | TARAK (GREEN PLY) | SAND | 2 TRIP
2 | 2022-05-02 | TARAK (GREEN PLY) | SAND | 25 BAG
3 | 2022-05-05 | TARAK (GREEN PLY) | SAND | 1 GARI
4 | 2022-05-07 | BANSAL TO GREEN PLY | SAND 3 TRIP | 75 BAG
5 | 2022-05-11 | JIYA TO G.PLY | SLIVER SAND | 400 FT
6 | 2022-05-18 | BANSAL TO GREEN PLY | SAND | 1 TRIP
7 | 2022-05-19 | JIYA TO GREEN PLY | SLIVER SAND | 400 FT
8 | 2022-05-19 | BANSAL TO GREEN PLY | CORE SAND | 25 BAG (1 TRIP)
9 | 2022-05-21 | BANSAL TO GREEN PLY | SAND | 25 BAG
SAND(JUNE)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2022-06-24 | BANSAL TO G.PLY | CORE SAND | 20 BAG (1 TRIP)
2
SAND(JULY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2022-07-04 | BANSAL TO GREEN PLY |  | 4 BAG
2 | 2022-07-10 | BANSAL TO GREEN PLY |  | 20 BAG
3 | 2022-07-19 | RAJU BUILDERS TO GREEN PLY |  | 10 BAG
4 | 2022-07-31 | BANSAL TO GREEN PLY |  | 25 BAG
SAND(AUG)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2022-08-15 | BANSAL TO GREEN PLY | SAND | 13 BAG
SAND(OCT) | [6 empty] | SAND(OCT)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT) |  |  | SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-10-03 | BANSAL TO G.PLY | SAND | 4 TRIP |  |  | 1 | 2022-10-08 | G.PLY TO BANSAL | SAND | 9 BAG
2 | 2022-10-04 | BANSAL TO G.PLY | SAND | 1 TRIP
3 | 2022-10-05 | TARAK BUILDERS TO G.PLY | SAND | 3 TRIP
4 | 2022-10-11 | BANSAL TO G.PLY | SAND | 10 BAG | TILL | 410 BAG
5 | 2022-10-15 | TETUL TALA TO G.PLY | SAND | 10 BAG |  | 800 CFT
6 | 2022-10-15 | TARAK BUILDERS TO G.PLY | SAND | 10 BAG
7 | 2022-10-16 | TARAK BUILDERS TO G.PLY | SAND | 15 BAG
SAND(NOV)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2022-11-06 | SALAPURIA TO G.PLY |  | 39 BAG
2 | 2022-11-12 | SALAPURIA TO G.PLY |  | 25 BAG
3 | 2022-11-17 | SALAPURIA TO G.PLY |  | 25 BAG
4 | 2022-11-17 | SALAPURIA TO G.PLY |  | 16 CFT
5 | 2022-11-18 | SALAPURIA TO G.PLY |  | 16 CFT
6 | 2022-11-19 | SALAPURIA TO G.PLY |  | 25 BAG
7 | 2022-11-20 | SALAPURIA TO G.PLY |  | 25 BAG
SAND(DEC)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2022-12-24 | SALAPURIA TO G.PLY |  | 20 BAG
2 | 2022-12-30 | SALAPURIA TO G.PLY |  | 10 BAG
3 | 2022-12-31 | SALAPURIA TO G.PLY |  | 20 BAG
SAND(JAN 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-01-01 | SALAPURIA TO G.PLY |  | 5 BAG
2 | 2023-01-08 | SALAPURIA TO G.PLY |  | 7 BAG
3 | 2023-01-16 | SALAPURIA TO G.PLY |  | 10 BAG
4 | 2023-01-22 | SALAPURIA TO G.PLY |  | 10 BAG
5 | 2023-01-26 | SALAPURIA TO G.PLY |  | 50 BAG
SAND(FEB 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-02-26 | TARAK BUILDER TO GREEN |  | 50 BAG
SAND(MAR 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-03-12 | SALAPURIA TO GREEN PLY |  | 25 BAG
2 | 2023-03-15 | SALAPURIA TO GREEN PLY |  | 12 BAG
SAND(APRIL 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-04-09 | RINKU BUILDERS TO GREEN PLY |  | 50 BAG
2 | 2023-04-16 | SALAPURIA TO GREEN PLY |  | 17 BAG
SAND(MAY 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-05-01 | RINKU BUILDERS TO GREEN PLY |  | 50 BAG
2 | 2023-05-25 | SALAPURIA TO GREEN PLY |  | 12 BAG
3 | 2023-05-27 | SALAPURIA TO GREEN PLY |  | 50 BAG
SAND(JUNE 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-06-04 | RINKU BUILDERS TO GREEN PLY |  | 15 BAG
2 | 2023-06-15 | SALAPURIA TO GREEN PLY |  | 50 BAG
3 | 2023-06-17 | SALAPURIA TO GREEN PLY |  | 25 BAG
4 | 2023-06-18 | SALAPURIA TO GREEN PLY |  | 25 BAG
5 | 2023-06-18 | SALAPURIA TO GREEN PLY |  | 25 BAG
6 | 2023-06-20 | SALAPURIA TO GREEN PLY |  | 50 BAG
7 | 2023-06-23 | SANTINIR TO GREEN PLY |  | 25 BAG
SAND(JULY 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-07-02 | SANTINIR TO GREEN PLY |  | 25 BAG
2 | 2023-07-18 | SANTINIR TO GREEN PLY |  | 10 BAG
3 | 2023-07-29 | RINKU BUILDERS TO GREEN PLY |  | 12 BAG
SAND(AUG-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-08-15 | RINKU BUILDERS TO GREEN PLY |  | 10 BAG
2 | 2023-08-20 | RINKU BUILDERS TO GREEN PLY 2NO |  | 50 BAG
3
SAND(SEP-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-09-05 | RINKU BUILDERS TO GREEN PLY |  | 10 BAG
2 | 2023-09-14 | RINKU BUILDERS TO GREEN PLY |  | 6 BAG
3 | 2023-09-15 | RINKU BUILDERS TO GREEN PLY 2NO |  | 25 BAG
4 | 2023-09-16 | RINKU BUILDERS TO GREEN PLY 2NO |  | 25 BAG
5 | 2023-09-20 | RINKU BUILDERS TO GREEN PLY 2NO |  | 15 BAG
6 | 2023-09-21 | RINKU BUILDERS TO GREEN PLY 2NO |  | 25 BAG
7 | 2023-09-24 | RINKU BUILDERS TO GREEN PLY 2NO |  | 25 BAG
8 | 2023-09-24 | RINKU BUILDERS TO GREEN PLY 2NO |  | 50 BAG
9 | 2023-09-24 | RINKU BUILDERS TO GREEN PLY 2NO | FLY ASH | 6TRIP
10 | 2023-09-25 | RINKU BUILDERS TO GREEN PLY 2NO |  | 20 BAG
11 | 2023-09-26 | RINKU BUILDERS TO GREEN PLY 2NO |  | 20 BAG
12 | 2023-09-29 | RINKU BUILDERS TO GREEN PLY 2NO |  | 10 BAG
SAND(OCT-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-10-05 | RINKU BUILDERS TO GREEN PLY 2NO |  | 20 BAG
2 | 2023-10-06 | RINKU BUILDERS TO GREEN PLY 2NO |  | 20 BAG
3 | 2023-10-21 | RINKU BUILDERS TO GREEN PLY |  | 25 BAG
4 | 2023-10-22 | RINKU BUILDERS TO GREEN PLY |  | 7 BAG
5 | 2023-10-25 | SS OFFICE TO GREEN PLY |  | 25 BAG
SAND(NOV-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-11-01 | AUSTIN TO GREEN PLY |  | 5 BAG
2 | 2023-11-10 | SS OFFICE TO GREEN PLY 2NO |  | 27 BAG
3 | 2023-11-11 | SS OFFICE TO GREEN PLY 2NO |  | 20 BAG
4 | 2023-11-17 | SS OFFICE TO GREEN PLY 2NO |  | 8 BAG
5
SAND(DEC-2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2023-12-17 | DALMIA TO GREEN PLY | SAND | 7 BAG
SAND(AUG-2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2024-08-04 | PURCHASE | SAND | 7 BAG
2 | 2024-08-11 | RAMKRISHNAPUR TO GREEN | SAND | 6 BAG
3 | 2024-08-15 | PAPPU TO GREEN | SAND | 25 BAG
4 | 2024-08-21 | PAPPU TO GREEN | SAND | 10 BAG
5 | 2024-08-23 | PAPPU TO GREEN | SAND | 20
6 | 2024-08-28 | LNB TO GREEN PLY | SAND | 4
7 | 2024-08-28 | RINKU TO GREENPLY | SAND | 25
SAND(SEP-2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2024-09-08 | RAMKRISHNAPUR TO GREEN | SAND | 25
SAND
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2025-11-06 | RINKU TO GP |  | 70
2 | 2025-11-07 | RINKU TO GP |  | 15 |  | 5
3 | 2025-11-09 | RINKU TO GP |  | 18 |  | 15
| 2025-11-15 | RINKU TO GP |  | 8 |  | 6
| 2025-11-17 | RINKU TO GP |  | 7
| 2025-12-31 | RINKU TO GP |  | 10
SAND
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2026-02-08 | SP TO GP |  | 7
| 2026-02-12 | SP TO GP |  | 8
| 2026-02-13 | RINKU TO GP |  | 25
| 2026-02-18 | SP TO GP |  | 6
| 2026-03-08 | SP TO GP |  | 20
| 2026-03-26 | Gaffer to gp |  | 20
| 2026-03-27 | Gaffer to gp |  | 75
| 2026-03-31 | PURCHASE |  | 25
| 2026-04-14 | mostofa to gp |  | 50
| 2026-04-15 | mostofa to gp |  | 50

## STONE
STONE(MAY)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
2 | 2022-05-01 | BANSAL TO GREEN PLY | 1 TRIP | ?
3 | 2022-05-07 | BANSAL TO GREEN PLY | 1 TRIP | 25 BAG
5 | 2022-05-21 | BANSAL TO GREEN PLY | 1 TRIP | 25 BAG
STONE(JULY)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2022-07-04 | BANSAL TO GREEN PLY |  | 4 BAG
2 | 2022-07-10 | BANSAL TO GREEN PLY |  | 13 BAG
3 | 2022-07-19 | RAJU BUILDERS TO GREEN PLY |  | 10 BAG
4 | 2022-07-31 | BANSAL TO GREEN PLY |  | 1 TRIP
STONE(AUG)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2022-08-15 | BANSAL TO GREEN PLY |  | 10 BAG
STONE(OCT) | [5 empty] | STONE(OCT)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG) |  | SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2022-10-03 | BANSAL TO GREEN PLY |  | 1 TRIP |  | 1 | 2022-10-08 | G.PLY TO BANSAL | STONE | 11 BAG
2 | 2022-10-11 | BANSAL TO GREEN PLY |  | 3 BAG | TILL
3 | 2022-10-14 | TETUL TALA TO G.PLY |  | 6 BAG
165 BAG
STONE(OCT)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2022-11-06 | BANSAL TO GREEN PLY |  | 39 BAG
2 | 2022-11-13 | BANSAL TO GREEN PLY |  | 25 BAG
STONE(NOV)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2022-11-18 | SALAPURIA TO GREEN PLY |  | 16 CFT
2
STONE(DEC)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2022-12-24 | SALAPURIA TO GREEN PLY |  | 20 BAG
2 | 2022-12-30 | SALAPURIA TO GREEN PLY |  | 8 BAG
STONE(JAN)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-01-22 | SALAPURIA TO GREEN PLY |  | 12 BAG
2 | 2023-01-26 | SALAPURIA TO GREEN PLY |  | 50 BAG
STONE(FEB)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-02-26 | BANSAL TO GREEN PLY |  | 50 BAG
STONE(MAR)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-03-15 | SALAPURIA TO GREEN PLY |  | 12 BAG
STONE(APRIL)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-04-09 | RINKU BUILDERS TO GREEN PLY |  | 50 BAG
2 | 2023-04-15 | SALAPURIA TO GREEN PLY |  | 10 BAG
STONE(MAY) | [5 empty] | STONE(MAY)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG) |  | SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-05-01 | RINKU BUILDERS TO GREEN PLY |  | 50 BAG |  | 1 | 2023-05-28 | GREEN PLY TO SANTINIR |  | 25 BAG
2 | 2023-05-25 | SALAPURIA TO GREEN PLY |  | 12 BAG |  | 2
3 | 2023-05-27 | SALAPURIA TO GREEN PLY |  | 40 BAG |  | 3
4 | 2023-05-28 | RINKU BUILDERS TO GREEN PLY |  | 25 BAG |  | 4
STONE(JUNE)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-06-12 | RINKU BUILDERS TO GREEN PLY |  | 25 BAG
2 | 2023-06-15 | RINKU BUILDERS TO GREEN PLY |  | 25 BAG
3 | 2023-06-17 | RINKU BUILDERS TO GREEN PLY |  | 25 BAG
4 | 2023-06-18 | RINKU BUILDERS TO GREEN PLY |  | 25 BAG
5 | 2023-06-18 | RINKU BUILDERS TO GREEN PLY | .5" | 15 BAG
6 | 2023-06-20 | RINKU BUILDERS TO GREEN PLY |  | 50 BAG
7 | 2023-06-25 | RINKU BUILDERS TO GREEN PLY | .5" | 8 BAG
STONE(JULY)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-07-29 | RINKU BUILDERS TO GREEN PLY |  | 12 BAG
STONE(AUG)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-08-15 | RINKU BUILDERS TO GREEN PLY |  | 10 BAG
2 | 2023-08-20 | RINKU BUILDERS TO GREEN PLY 2NO | 1/2" | 10 BAG
STONE(OCT)
SR NO | DATE | FROM WHERE TO WHERE | SIZE | DETAILS (KG)
1 | 2023-10-21 | RINKU BUILDERS TO GREEN PLY |  | 25 BAG
2 | 2023-10-22 | RINKU BUILDERS TO GREEN PLY |  | 7 BAG
SAND(AUG-2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2024-08-11 | RAMKRISHNAPUR TO GREEN |  | 6
2 | 2024-08-15 | PAPPU TO GREEN |  | 4
3 | 2024-08-21 | PAPPU TO GREEN | 1*2 | 5
4 | 2024-08-26 | RAMKRISHNAPUR TO GREEN |  | 10
SAND(SEP-2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (FT)
1 | 2024-09-08 | RAMKRISHNAPUR TO GREEN |  | 15
2
3
4
NEW PHASE - NOV -25
SAND
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (BAG)
1 | 2025-11-05 | BISHNUPUR TO GP |  | 10
2 | 2025-11-05 | GP GODOWN TO GP |  | 11
3 | 2025-11-06 | RINKU TO GP |  | 3
4 | 2025-11-07 | RINKU TO GP |  | 15
5 | 2025-11-09 | RINKU TO GP |  | 27
6 | 2025-11-17 | RINKU TO GP |  | 12
| 2026-02-13 | Sp to Gp |  | 30
| 2026-03-25 | Sp to Gp |  | 20
| 2026-03-27 | Arun to gp |  | 30
| 2026-03-29 | purchase |  | 25
| 2026-03-31 | purchase |  | 50
| 2026-04-15 | purchase |  | 6

## BRICKS
BRICKS(APRIL)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
6 | 2022-04-28 | BANSAL TO G.PLY | RAJU TEMPO | 333
7 | 2022-04-29 | BANSAL TO G.PLY |  | 333
BRICKS(MAY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-05-05 | TARAK (GREEN PLY) | ? | 300
2 | 2022-05-17 | BISHNUPUR TO G.PLY | PAPER BLOCK | 70 PCS
3 | 2022-05-29 | BISHNUPUR TO G.PLY | PAPER BLOCK | 125 PCS
BRICKS(JUNE)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-06-11 | BISHNUPUR TO G.PLY | PAPER BLOCK | 160 PCS
2 | 2022-06-24 | BANSAL TO G.PLY | RAJU TEMPO | 350 PCS
BRICKS(JULY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-07-10 | BISHNUPUR TO G.PLY | PAVER BLOCK | 50 P
BRICKS(AUG)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-08-18 | BISHNUPUR TO G.PLY | PAVER BLOCK | 30
BRICKS(OCT)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-10-03 | G.PLY | PAVER BLOCK | 2240 | TILL
2 | 2022-10-14 | TETUL TALA TO G.PLY | BRICKS | 60
3 | 2022-10-15 | TETUL TALA TO G.PLY | BRCKS | 150
4 | 2022-10-15 | TETUL TALA TO G.PLY | PAVER BLOCK | 150
5 | 2022-10-15 | TARAK BUILDERS TO G.PLY | BRICKS | 100
6 | 2022-10-22 | G.PLY | ZIG ZAG | 980P | 80MM
|  | TOTAL BRICK | 3991 P
BRICKS(NOV)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-11-19 | SALAPURIA TO GREEN PLY |  | 350P
2 | 2022-11-20 | SALAPURIA TO GREEN PLY |  | 333P
3
BRICKS(DEC)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-12-16 | SALAPURIA TO GREEN PLY | SLAB | 14P
BRICKS(JAN 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-01-01 | SALAPURIA TO GREEN PLY |  | 70 P
2 | 2023-01-08 | SALAPURIA TO GREEN PLY |  | 100P
3 | 2023-01-17 | SALAPURIA TO GREEN PLY |  | 50 P
BRICKS(MAR 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-03-19 | SALAPURIA TO GREEN PLY |  | 300P
2
3
BRICKS(MAY 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-05-24 | RINKU TO GREEN PLY |  | 333P
2
3
BRICKS(JUNE 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-06-21 | SALAPURIA TO GREEN PLY |  | 150P
2
3
BRICKS(AUG- 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-08-20 | GREEN PLY DOSTUPUR | BATS | 791 CFT
2 | 2023-08-20 | SS TO GREEN PLY 2NO | PAVER BLOCK | 220P
3 | 2023-08-23 | GREEN PLY DOSTUPUR | BATS | 823 CFT
BRICKS(SEP- 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-09-05 | RINKU TO GREEN PLY | BRICKS | 200
2 | 2023-09-13 | GREEN PLY DOSTUPUR | BATS | 718 CFT
3 | 2023-09-20 | RINKU BUILDERS TO GREEN PLY 2NO | BRICKS | 200
4 | 2023-09-29 | GREEN PLY DOSTUPUR | BATS | 739 CFT
5 | 2023-09-29 | RINKU BUILDERS TO GREEN PLY 2NO | BRICKS | 300
BRICKS(OCT- 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-10-02 | RINKU TO GREEN PLY | BRICKS | 100
2 | 2023-10-05 | RINKU TO GREEN PLY | BRICKS | 300
3 | 2023-10-06 | RINKU TO GREEN PLY | BRICKS | 100
4 | 2023-10-18 | RINKU TO GREEN PLY | BRICKS | 666
5 | 2023-10-20 | GREEN PLY QUARTER RECIVE | PAVER BLOCK | 1800
6 | 2023-10-21 | RINKU TO GREEN PLY | BRICKS | 333
BRICKS(NOV- 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-11-01 | AUSTIN TO GREEN PLY |  | 160
BRICKS(NOV- 2023)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-12-17 | GREEN PLY QUARTER RECIVE | PAVER BLOCK | 125
BRICKS(AUG- 2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2024-08-04 | PRABITRA TO PAVER BLOCK |  | 200
BRICKS(SEP- 2024)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2024-09-08 | RAMKRISHNAPUR TO GREENPLY |  | 100
BRICKS - 2025
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2025-12-01 | RINKU TO GP |  | 150

## OTHER'S
OTHER'S(DEC)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2022-12-24 | GREEN PLY TO SALAPURIA | PLY | 90P
2 | 2022-12-30 | SALAPURIA TO GREEN PLY | SIKA (OIL) | 1/2 LTR
|  |  | BAINDING WIRE | 1.5 KG
OTHER'S(FEB)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-02-05 | GREEN PLY TO SALAPURIA | VIVADOR | 3P
|  |  | WIRE , CORA | 1P
LADDER , BAMBOO
OTHER'S(APRIL)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-04-09 | SS OFFICE TO GREEN PLY | BOSTA | 20P
OTHER'S(MAY)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-05-10 | SS OFFICE TO GREEN PLY | M.S PALLATE | 4P -8'1"*4'2"
OTHER'S(AUG)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-08-03 | GREEN PLY | SELF | 500P
OTHER'S(SEP)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-09-26 | GREEN PLY 2NO | RED PRIMER | 3LTR
OTHER'S(OCT)
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2023-10-10 | SS TO GREEN | EMPTY BAG | 100P
JCB
SR NO | DATE | FROM WHERE TO WHERE | BRAND | DETAILS (PCS)
1 | 2026-03-25 | JCB | 7.5 H
2 | 2026-03-29 | JCB | 4.5 H
| 2026-03-29 | Dumper |  | oil 45 ltr - 4144.50/-
| 2026-03-31 | JCB | 6.5 H
| 2026-04-01 | JCB | 11 H
| 2026-04-04 | Salbollah | 51 p
| 2026-04-10 | color purchase (metal -4l primer -2ltr) |  | 700
| 2026-04-13 | Salbollah | 60 | 38700
| 2026-04-15 | TILES |  | 380
|  | BLADE |  | 120
|  | COLOOUR |  | 200
| 2026-04-18 | Salbollah | 40
| 2026-04-21 | JCB | 8H | 2300
|  | Salbollah | 60 | 41000 | JIYA
| 2026-04-22 | Salbollah | 60
| 2026-04-23 | Salbollah | 60
| 2026-04-24 | Salbollah | 60
| 2026-04-26 | Salbollah | 60
| 2026-04-27 | Salbollah | 35
| 2026-05-06 | Tiles -3 Box | 3 | 1140
| 2026-05-17 | Poclain | in
| 2026-05-18 | Pump | 1 | Oil-356
| 2026-05-18 | Poclain | Road clean
| 2026-05-19 | Poclain | Read - 9412.5 | oil - 2449/-
| 2026-05-26 | Batam | 160 - Pcs
| 2026-05-27 | Batam | 200 - pcs

## SUMMERY
Sum of QTY
PRODUCT CATEGORY | UNIT | Total
BRICKS | PIECE | 333 | SL NO | PRODUCT CATEGORY | UT | UNIT | Total | RATE | AMOUNT
SAND | BAG | 252 | 1 | BRICKS |  | PIECE | 333 | 11 | 3663
STONE | BAG | 227 | 2 | SAND |  | BAG | 252 | 100 | 25200
STONE .5" | BAG | 15 | 3 | STONE |  | BAG | 227 | 120 | 27240
TMT 14' | PIECE | 10 | 4 | STONE .5" |  | BAG | 15 | 100 | 1500
TMT 14.6' | PIECE | 22 | 5 | TMT 14' | 14 | PIECE | 10 |  | 0 | 140
TMT 6' | PIECE | 27 | 6 | TMT 14.6' | 14.6 | PIECE | 22 |  | 0 | 321.2
TMT 6.6' | PIECE | 22 | 7 | TMT 6' | 6 | PIECE | 27 |  | 0 | 162
TMT 7' | PIECE | 74 | 8 | TMT 6.6' | 6.6 | PIECE | 22 |  | 0 | 145.2
ULTRATECH | BAG | 73 | 9 | TMT 7' | 7 | PIECE | 74 |  | 0 | 518
TMT 16MM | PIECE | 5 | 10 | ULTRATECH |  | BAG | 73 | 350 | 25550
Grand Total |  | 1060 | 11 | TMT 16MM |  | PIECE | 5 |  | 0
|  |  | 12 | TMT KG (TOTAL) |  | KG | 500 | 72 | 36000
|  |  |  | Grand Total |  |  | 1060 |  | 119153 | 1286.4
32.16

## 12.05 TO 20.06
12.05 TO 20.06
PRODUCT | DATE | PARTICULAR | PRODUCT CATEGORY | QTY | UNIT
CEMENT | 2023-05-25 | SALAPURIA TO GREEN PLY | ULTRATECH | 3 | BAG
CEMENT | 2023-05-28 | RINKU TO GREEN PLY | ULTRATECH | 7 | BAG
CEMENT | 2023-06-04 | RINKU TO GREEN PLY | ULTRATECH | 5 | BAG
CEMENT | 2023-06-12 | RINKU TO GREEN PLY | ULTRATECH | 4 | BAG
CEMENT | 2023-06-15 | RINKU TO GREEN PLY | ULTRATECH | 12 | BAG
CEMENT | 2023-06-17 | RINKU TO GREEN PLY | ULTRATECH | 12 | BAG
CEMENT | 2023-06-18 | RINKU TO GREEN PLY | ULTRATECH | 10 | BAG
TMT | 2023-05-26 | SALAPURIA TO GREEN PLY | TMT 16MM | 5 | PIECE
SAND | 2023-05-25 | SALAPURIA TO GREEN PLY | SAND | 12 | BAG
SAND | 2023-05-27 | SALAPURIA TO GREEN PLY | SAND | 50 | BAG
SAND | 2023-06-04 | RINKU BUILDERS TO GREEN PLY | SAND | 15 | BAG
SAND | 2023-06-15 | SALAPURIA TO GREEN PLY | SAND | 50 | BAG
SAND | 2023-06-17 | SALAPURIA TO GREEN PLY | SAND | 25 | BAG
SAND | 2023-06-18 | SALAPURIA TO GREEN PLY | SAND | 25 | BAG
SAND | 2023-06-18 | SALAPURIA TO GREEN PLY | SAND | 25 | BAG
STONE | 2023-05-25 | SALAPURIA TO GREEN PLY | STONE | 12 | BAG
STONE | 2023-05-27 | SALAPURIA TO GREEN PLY | STONE | 40 | BAG
STONE | 2023-05-28 | RINKU BUILDERS TO GREEN PLY | STONE | 25 | BAG
STONE | 2023-06-12 | RINKU BUILDERS TO GREEN PLY | STONE | 25 | BAG
STONE | 2023-06-15 | RINKU BUILDERS TO GREEN PLY | STONE | 25 | BAG
STONE | 2023-06-17 | RINKU BUILDERS TO GREEN PLY | STONE | 25 | BAG
STONE | 2023-06-18 | RINKU BUILDERS TO GREEN PLY | STONE | 25 | BAG
STONE | 2023-06-18 | RINKU BUILDERS TO GREEN PLY | STONE .5" | 15 | BAG
BRICKS | 2023-05-24 | RINKU TO GREEN PLY | BRICKS | 333 | PIECE
TMT | 2023-06-13 | SS OFFICE TO GREEN PLY | TMT 14' | 10 | PIECE
TMT | 2023-06-13 | SS OFFICE TO GREEN PLY | TMT 6' | 27 | PIECE
TMT | 2023-06-13 | SS OFFICE TO GREEN PLY | TMT 7' | 74 | PIECE
TMT | 2023-06-13 | SS OFFICE TO GREEN PLY | TMT 14.6' | 22 | PIECE
TMT | 2023-06-13 | SS OFFICE TO GREEN PLY | TMT 6.6' | 22 | PIECE
SAND | 2023-06-20 | SALAPURIA TO GREEN PLY | SAND | 50 | BAG
STONE | 2023-06-20 | RINKU BUILDERS TO GREEN PLY | STONE | 50 | BAG
CEMENT | 2023-06-20 | RINKU BUILDERS TO GREEN PLY | ULTRATECH | 20 | BAG
| 2023-05-28 | GREEN PLY TO SANTINIR | STONE | 25 BAG

## DUMPER
DUMPER - DETAILS GREENPLY WORK
[7 empty] | SITE ADVS |  | OFFICE ADVS
SL NO | DATE | DESCRIPTION | DUMPER NO | QTY | UNIT | KM (UP-DOWN) | OIL | DRIVER ADVS | DATE | AMOUNT | REMAKRS
1 | 2026-05-19 | DUMPER | 5422 | 4 | TRIP | 112 | 2500 | 500 | 2026-05-20 | 5000
2 | 2026-05-19 | DUMPER | 1228 | 4 | TRIP | 112 | 2500 | 500 | 2026-05-22 | 10000
3 | 2026-05-20 | DUMPER | 5422 | 3 | TRIP | 84 | 2500 | 500 | 2026-05-27 | 16000
4 | 2026-05-21 | DUMPER | 5422 | 4 | TRIP | 112 | 2500 | 500
5 | 2026-05-22 | DUMPER | 5422 | 3 | TRIP | 84 | 2500 | 500
6 | 2026-05-26 | DUMPER | 6715 | 5 | TRIP | 64 | 4000 | 500
7 | 2026-05-26 | DUMPER | 6315 | 5 | TRIP | 64 | 4000 | 500
8 | 2026-05-26 | DUMPER | 9591 | 4 | TRIP | 55 | 3000 | 500
9 | 2026-05-26 | DUMPER | 5422 | 5 | TRIP | 64 | 3000 | 500
10 | 2026-05-26 | DUMPER | 8933 | 4 | TRIP | 55 | 3000 | 500
11 | 2026-05-31 | DUMPER |  | 7 | TRIP
TOTAL |  |  |  | 48 |  |  | 29500 | 5000 |  | 15000
POCLAIN - DETAILS GREENPLY WORK
[7 empty] | SITE ADVS |  | OFFICE ADVS
SL NO | DATE | DESCRIPTION | READING | QTY | UNIT |  | OIL | DRIVER ADVS | DATE | AMOUNT | REMAKRS
1 | 2026-05-19 | POCLAIN | 9412.5 - 9419.2 | 6 H 42 MIN | HOUR |  | 7100 |  | 2026-05-26 | 20000
3 | 2026-05-20 | POCLAIN | 9419.2 - 9419.8 | 36 MIN | HOUR |  | 2500
4 | 2026-05-21 | POCLAIN | 9419.8 -9421.0 | 1 H 12 MIN | HOUR |  | 2500
5 | 2026-05-22 | POCLAIN | 9421.0 - 9421.9 | 54 MIN | HOUR |  | 2500
6 | 2026-05-26 | POCLAIN | 9421.9 - 9426.9 | 5 H | HOUR |  | 5000 | 150
7 | 2026-05-31 | POCLAIN
TOTAL |  |  |  | 14 H 40 MIN |  |  | 19600 | 150 |  | 20000

## 35D HOT PRESS
35 D Hot Press
Till Date - 22.06.26
Sl No | Description | Unit | Qty | Rate | Amount | Remarks
1 | JCB | Hour | 97.5 | 1200 | 117000
2 | Dumper | Days | 2 | 6000 | 12000
3 | Salballah | pcs | 686 | 720 | 493920
4 | Lab | Head | 278 | 700 | 194600
5 | Salballah fixing | pcs | 686 | 350 | 240100
6 | Dumper - Dostipur | Trip | 32 | 3500 | 112000
7 | Dumper - Matalthes | Trip | 24 | 3500 | 84000
8 | Poclain | - | - | L/S | 80000
9 | Other's Exp | - | - | L/S | 35000
10 | De-Watering | - | - | L/S | 25000
11 | Night Lab for De-Watering | Head | 20 | 800 | 16000
Total : |  |  |  |  | 1409620